## Risk Register
Risk Id | Risk Description | Impact | Probability | Category | Risk raised by | Risk raised date | Allocated to | Due date | Status | Action | Response
R-001 | LMS portal producing slow load times | More number of complain register | 80% | Technology | Ram karan | 23 June,2026 | Saphal | 4 August,2026 | Closed | Optimize database queries and media compression | Mitigate
R-002 | Privacy data breach | Data loss or rules break | 10% | Data | Hari | 23 June,2026 | Saphal | 4 August,2026 | Assigned | Implementing strong encryption | Prevent
R-003 | Website glitch | Less user flow | 40% | Technology | Sudhan | 23 June,2026 | Saphal | 3 August,2026 | Open | Use best cloud computing | Prevent
R-004 | Cloud hosting server downtime | No information flow | 30% | Technology | Suresh | 24 June,2026 | Saphal | 4 August,2026 | Open | Deploy multi-region cloud backup architecture | Mitigate
R-005 | Poor user experience | People not liking UX design | 40% | people | Hari | 24 June,2026 | Saphal | 4 August,2026 | Closed | Conduct testing | Mitigate
R-006 | Lack of trained LMS administrators | Delayed onboarding timelines for content creators | 30% | People | Sudhan | 23 June,2026 | Saphal | 5 August,2026 | Open | Launch specialized training documentation hub | Mitigate
R-007 | Data quality issue | Getting less favourable output | 10% | Technology | Samar | 25 June,2026 | Jen's | 4 August,2026 | Open | Cleaning datasets and validation | Mitigate
R-008 | Third party dependency risks | Financial losses | 20% | Data | Sudhan | 23 June,2026 | Jen's | 4 August,2026 | Open | Reduce reliance | Prevent
R-009 | Delays in custom theme development | Missed institutional branding launch target | 40% | Requirements | Sudhan | 25 June,2026 | Jen's | 5 August,2026 | Open | Consult with Hr | Prevent
R-010 | Legal compliance issues | Suffering in implementation of regulation and laws | 40% | Requirements | Hari | 23 June,2026 | Saphal | 4 August,2026 | Open | Utilize core platform features until code ready | Prevent
R-011 | Delays in development timeline | Project not completing in time | 70% | Requirements | Ram karan | 23 June,2026 | Jen's | 4 August,2026 | Open | Agile Sprint planning | Prevent
R-012 | Security vulnerabilities | Hack attacks | 50% | Technology | Sudhan | 24 June,2026 | David | 3 August,2026 | Open | Regular security audits | Prevent
R-013 | Budget overrun | Going more than budget in few development goals | 70% | people | Sudhan | 24 June,2026 | Saphal | 3 August,2026 | Open | Strick cost tracking and approvals | Prevent
R-014 | Team member leaving unhappy | May affect other or might create conflicts | 80% | people | Samar | 23 June,2026 | David | 4 August,2026 | Open | Don't do anything | Ignore
R-015 | Performance issue | Poor performance in low end | 30% | Technology | Sudhan | 26 June,2026 | Jen's | 2 August,2026 | Open | Optimise backend | Prevent
R-016 | Undocumented growth | Affecting the original plan | 30% | Data | Sudhan | 23 June,2026 | Saphal | 4 August,2026 | Closed | Change control | Prevent

## Issue Register
Issue Id | Issue Description | Impact | Probability | Category | Issue raised by | Issue raised date | Allocated to | Due date | Status | Action | Response
Id-001 | Learning resources error | Impact on user flow | 100% | Technology | Sudhan | 23 June,2026 | Jen's | 4 August,2026 | Open | Retrain model and adjust prompt | Address
Id-002 | Developer don't know python | Project quality suffer | 100% | People | Sudhan | 23 June,2026 | Jen's | 4 August,2026 | Open | Train them | Address
Id-003 | Website loading slow | User experience | 70% | Technology | Sudhan | 23 June,2026 | Jen's | 3 August,2026 | Open | Optimise code and server | Address
Id-004 | Attackers can attack on week page | Data breaches, server disruption | 80% | People | Sudhan | 24 June,2026 | Jen's | 4 August,2026 | Open | Optimise and clear vulnerabilities | Address
Id-005 | Site freeze | High user frustration | 50% | Technology | Hari | 24 June,2026 | Saphal | 4 August,2026 | Open | Site optimisation | Address
Id-006 | Site cannot performed scheduled action | Reduced business benefits | 40% | Technology | Ram | 23 June,2026 | Jen's | 5 August,2026 | Open | Testing API connection | Address
Id-007 | PDF file missing the company logo | File team not clear | 80% | Technology | Sudhan | 25 June,2026 | Jen's | 4 August,2026 | Open | Use a proper link for logo print | Address
Id-008 | Not using copyright items | Copyright lawsuits | 60% | Technology | Ram | 23 June,2026 | Saphal | 4 August,2026 | Open | Get legal permission to upload | Address
Id-009 | Lack to measures not actual business value | Waste of budget | 80% | Technology | Sudhan | 25 June,2026 | Jen's | 5 August,2026 | Open | Using real time dashboard and clear KPIs. | Address
Id-010 | Bot failing to remember previous message | High user frustration | 90% | People | Sudhan | 23 June,2026 | Jen's | 4 August,2026 | Open | Using slot filling and multi dialogue management | Address
Id-011 | Attacker exploiting token to run APIs | Unpredictable financial loss | 80% | Technology | Sudhan | 23 June,2026 | Jen's | 4 August,2026 | Open | Set strict rate limits on real time cost limits | Address
Id-012 | Delay in feature delivery | Upset stake holder | 80% | People | Sudhan | 24 June,2026 | Jen's | 3 August,2026 | Open | Add resources and drop extra features | Address
Id-013 | Poor communication among team | Missed requirements | 100% | People | Sudhan | 24 June,2026 | Jen's | 3 August,2026 | Open | Clarify roles and centralised documents | Address
Id-014 | Missing project documentation | Support failure and unable to fixed bugs | 100% | Data | Hari | 23 June,2026 | Saphal | 4 August,2026 | Open | Audits current gaps and assigned docs | Address
Id-015 | Training materials not ready | Negative initial reviews | 90% | People | Ram | 26 June,2026 | Saphal | 2 August,2026 | Open | Delay launch | Address
Id-016 | Minor UI inconsistency | Doesn't stop user interaction | 40% | People | Hari | 23 June,2026 | Jen's | 4 August,2026 | Closed | Add to low priority | Ignore